## Laura
Name: Laura Kocubinski
Lead Roles: Team Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/6 - 9/13 | #NAME? | #NAME? | 1 | 0 - Read and took notes on book chapters 1 - 4 1 - Read and took notes on book chapters 10 & 11; joined Pivotal Tracker 5 - Joined Slack, copied/configured project documents (including this one) to Team 2 Google Docs, prepped agenda for kickoff meeting 6 - Setup GitHub Desktop client, committed team.md to Lab1 branch | 8 | 2 |  |  |  | 2 | 0.5 | 0.5 | 1. Joined GitHub and commited change to team.md to Lab1 branch 2. Joined Pivotal Tracker |  |  | 0 - Read chapters 13 - 15 1 - Define requirements and user stories, add to SPP 6 - Find time for a recurring team meeting | 10
2 | 9/13 - 9/20 | #NAME? | #NAME? | 2 | 0 - Read and took notes on book chapters 7 - 9 5 - Surveyed team members for weekly recurring group meeting, created agenda for 9/15 team meeting, organize and send out action items 7 - Completed 'Management Plan' in SPPP, created presentation outline for group, reviewed SPPP, responding the emails, faciliating slack communication | Time Spent [h] Task 0: 2; Time Spent [h] Task 5: 1; Time Spent [h] Task 7: 11 | 1. Completed 'Management Plan' in SPPP 2. Created presentation for iteration 0 3. Created risk management workbook 4. Created project schedule | 1. Group communication is not good |  | 0 - Help setup server, database, and backend | 10

## Xi
Name: Xi You
Lead Roles: QA Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/6 - 9/13 | 0
2 | 9/13 - 9/20 | 0

## Misha
Name: Misha Chertushkin
Lead Roles: Security Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/6 - 9/13 | 0
2 | 9/13 - 9/20 | 0

## Beven
Name: Beven Liu
Lead Roles: Configuration Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/6 - 9/13 | 0
2 | 9/13 - 9/20 | 8 | 7 | 1 | 0 - Learned Git/GitHub, Python; Review lecture notes 6 - Set up project tools: Slack, GitHub, Pivotal tracker, Zoom, etc. Set environment: Python 7 - Complete the part of Configuration Management Plan in SPPP. | Time Spent [h] Task 0: 4; Time Spent [h] Task 6: 1; Time Spent [h] Task 7: 2 | 1 - Finish part of SPPP |  |  | 1 - Keep learning Python 2 - Keep reviewing lecture notes and reading textbook 3 - Start to learn web development(Not sure) | 8

## Jhuanderson
Name: Jhuanderson Macias
Lead Roles: Backup Project Leader, Requirement Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/6 - 9/13 | 2 | 1 | 1 | 5 - Setup Slack workspace, set up Pivotal Tracker 6 - Create Team 2 Respository on Github Clone folder and set up path and enviroment within person computer. pushed team.md commit to Lab1 branch 7 - Search for ideas involving communication. | Time Spent [h] Task 5: 0.25; Time Spent [h] Task 6: 0.25; Time Spent [h] Task 7: 0.5 | 1. Pushed team.md commit to Lab1 branch 2. Joined and learned Pivotal Tracker |  |  | 0 - Read chapters 13 - 15 1 - Define requirements and user stories, add to SPP 6 - Find time for a recurring team meeting | 5
2 | 9/12 - 9/18 | 4 | 2 | 2 | 0 - rearched Frameworks and BackEnd Configurations | Time Spent [h] Task 0: 2
3 | 9/19 - 9/25 | 13 | 12 | 1 | 0 - reasearch development vs prodcution enviroments 0- research real world exmaples by talking to software engineers about their process for devlopment 0 - research framework integrations 0 - reasearch databases - NOSQL vs SQL and its affects with our stack 6 - Created Docker enviroment that will be used for dev. ops 4 - Research Integrating testing tool (Jenkins) and its Integration with AWS 3 - started to build out simple protype of chat communication | Time Spent [h] Task 0: 4; Time Spent [h] Task 3: 2; Time Spent [h] Task 4: 1; Time Spent [h] Task 6: 5 | Basic Prototpy of Communciation tool Framework Set up Shared Resorces

## Hang
Name: Hang Shi
Lead Roles: Backup Team Leader, Requirements Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/6 - 9/13 | 11 | 10 | 1 | 0 - learn from blackboard and list all element needed in this course 1 - set up team github and joined Pivotal Tracker and google drive 4 - Group github manage and verify access testing 5 - Join Slack team group, set up zoom video meeting configuration 6 - Setup GitHub Desktop client, committed team.md to Lab1 branch, add extra branch for team code testing and delete when we all finish, allocate all information on github quicktips.md for easily record and manage | 2 | 1 | 2 |  | 1 | 0.5 | 3.5 |  | 1 - Create github group 2 - Verify github group acess 3 - Compare and consider object of develop 4 - Test and create new branch for testing 5 - Merge and delete useless branch when all finish lab1 6 - Configuration help |  |  | 0 - learn from blackboard and relearn the github and web deisgn 1 - fill the SPPP requirement part and check more develop requirement 4 - Group github manage and merge test branch 5 - renew the allert in Slack avoid now receive messgae from group channel 6 - test and find out which platform or language using is best for group work | 10
2 | 9/13 - 9/20 | 7 | 7 | 0 | 0 - learn from blackboard and relearn the github and web deisgn 1 - fill the SPPP requirement part and check more develop requirement 4 - Group github manage and merge test branch 5 - renew the allert in Slack avoid now receive messgae from group channel 6 - test and find out which platform or language using is best for group work | 2 | 1 |  |  | 1 | 0.5 | 2.5 |  | 1 - Check the requirement for SPPP 2 - Analysis functional and nofunctional requirement 3 - Help finish slide and SPPP 4 - Update github group record 5 - Create new branch for testing | own problem not join group discussion but see record and finish my part

## Metrics-GroupIterationProgress
Iteration | Start Date - End Date | # of User Stories Completed | # of User Stories in Progress | # of Issues Opened | # of Issues Closed | # of Issues Remaining | Time [h]
[7 empty] | Total | Individual Work | Group Meeting | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6
0 | 9/6 - 9/20
1
2
3
4
5

## Summary-GroupIterationProgress
Iteration | Start Date - End Date | Accomplishment Summary (i.e. User Stories, Tasks Completed, Big Progress, Good Practices Used, etc.) | Technical Issues Summary | Non-Technical Issues Summary | Process Improvement/Plan
0 | 09/6 - 9/20
1
2
3
4
5