## Project Risk Status
ID | Risk Category | Risk Title | Risk Description | Owner | Probability [1-3] | Severity [1-3] | Risk Level [1-9] | Retirement Cost [h] | Mitigation Plan | Target Closure Date | Status [Open or Closed] | Notes
1 | Personel | Loss of team members | One or more students may drop the class and leave the team | - | 2 | 2 | 4 | 0 | Another team member assumes role of the lost teammate | 2019-10-07 | Open | 10/7 is last day to drop a class without a W
2 | Personel | Adding new team member | One or more students may join the class team and join the team | - | 2 | 1 | 2 | 0 | Give new team member one of the duplicate roles | 2019-09-16 | Open | 9/16 is last day to add a class
3 | Management | Lack of motiviation or responsbility | One or more students may not contribute as expected to the project | - | 2 | 2 | 4 |  |  | 2019-10-01 | Open
4 | Communication | Not familiar with QA
5 | Technolgy Competence | Not familiar with security
6 | Technolgy Competence | Not familiar with testing
7 | Technolgy Competence | Not familiar with GitHub
8 | Technolgy Competence | Not familiar with web or app development
9 | Technolgy Competence | Not familiar with programming language
xx

## Risk Rating Criteria
Risk Rating Criteria
Probability |  |  | Severity
Rating | Likelihood | Description | Rating | Impact | Description
1 | Rare or Unlikely | Could occur at some point | 1 | Minor | Minor impact to project
2 | Possible | Might occur at some point | 2 | Moderate | Some impact to project
3 | Likely or Very Likely | Will likely occur at some point | 3 | Major | Major impact to project

## Risk Categories
Risk Categories
Management
Implementation
Testing
Integration
Deployment Rush
Specific Technical Issues
Improper Scope
Requirements
Communication
Personel
Technology Competence