## Laura
Name: Laura Kocubinski
Lead Roles: Team Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/5 - 9/11 | 14 | 13 | 1 | 0 - Read and took notes on book chapters 1 - 4 1 - Read and took notes on book chapters 10 & 11; joined Pivotal Tracker 5 - Joined Slack, copied/configured project documents (including this one) to Team 2 Google Docs, prepped agenda for kickoff meeting 6 - Setup GitHub Desktop client, committed team.md to Lab1 branch | 8 | 2 |  |  |  | 2 | 0.5 | 0.5 | 1. Joined GitHub and commited change to team.md to Lab1 branch 2. Joined Pivotal Tracker |  |  | 0 - Read chapters 13 - 15 1 - Define requirements and user stories, add to SPP 6 - Find time for a recurring team meeting | 10
2 | 9/12 - 9/18 | 16 | 14 | 2 | 0 - Read and took notes on book chapters 7 - 9 5 - Surveyed team members for weekly recurring group meeting, created agenda for 9/15 team meeting, organize and send out action items 7 - Completed 'Management Plan' in SPPP, created presentation outline for group, reviewed SPPP, responding the emails, faciliating slack communication | Time Spent [h] Task 0: 2; Time Spent [h] Task 5: 1; Time Spent [h] Task 7: 11 | 1. Completed 'Management Plan' in SPPP 2. Created presentation for Iteration 0 3. Created risk management workbook 4. Created project schedule | 1. Group communication is not good |  | 0 - Help setup server, database, and backend | 10
3 | 9/19 - 9/25 | 19.5 | 19.5 | 0 | 0 - Research AWS; read book chapters on design and testing; went through few tutorials on Django to build skeleton of web app https://www.youtube.com/watch?v=UmljXZIypDc&list=PL-osiE80TeTtoQCKZ03TU5fNfx2UY6U4p (videos 1 - 6) https://www.youtube.com/watch?v=Wv5jlmJs2sU 1 - Created user stories in Pivotal Tracker 3 - Created AWS account; setup Elastic Beanstalk for Python web application; gave group members access; created registration/login/logout functionality for website; created skeleton 5 - Created and prioritized tasks; communicated tasks and deadlines to team members; updated SDD, STD 6 - Setup Docker on Mac | 4 | 1 | 10 |  |  | 4 | 0.5 |  | 1. Created skeleton for web application with Joe | 1. Nobody joined Sunday's group meeting 2. Only one person resonded to my request for a makeup meeting 3. I only get a response from one or two people in Slack 4. I can't get in touch via email or Slack with other members to communicate the work to be done |  | 7 - Update SPP, draft SDD and STD, write test code, work on presentation | 15
4 | 9/26 - 10/2 | 12.5 | 11.5 | 1 | 1 - Created registration, login/logout, reset password user stories (Lab 2) 2 - Created icon, help to review to database schema and deploy on AWS 3 - Created AWS PostgreSQL database; altered security group setting so we can now successfully connect to database for table creation, etc. 5 - Delegate tasks to team members 6 - Updated project README.md, logged few issues in GitHub Issue tracker 7 - Update SPPP, SDD, Iteration 1 Presentation, Group Progress Report, Risk Management Worksheet |  | 1 | 0.5 | 1 |  | 1 | 1 | 7 | 1. Updated SPPP, GitHub README.md 2. Drafted SDD 3. Created Iteration 1 presentation |  |  | 3 - Resolve issues assigned to me 7 - Draft STD | 10

## Xi
Name: Xi You
Lead Roles: QA Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/5 - 9/11 | 8 | 8 |  | 0 - learn from blackboard and list all element needed in this course 1 - set up team github and joined Pivotal Tracker and google drive 5 - Join Slack team group, set up zoom video meeting configuration 6 - Setup GitHub Desktop client, committed team.md to Lab1 branch | Time Spent [h] Task 0: 4; Time Spent [h] Task 1: 1.5; Time Spent [h] Task 5: 1; Time Spent [h] Task 6: 0.5 | 1 - Join github group 2 - Verify github group acess 3 - Compare and consider object of develop 4 - modify team.md
2 | 9/12 - 9/18 | 10 | 8 | 2 | 0 - learn from blackboard and learn QA acknowledge 1 - fill the SPPP requirement part and presentation 5 - communicate with teammates 6 - research flask | Time Spent [h] Task 0: 4; Time Spent [h] Task 1: 1; Time Spent [h] Task 5: 2; Time Spent [h] Task 6: 3 | 1 - fill my part of SPPP 2 - research flask 3 - Help finish slide and SPPP
3 | 9/19 - 9/25 | 10 | 9 | 1 | 0 - watching the django tutorial 1 - Created user stories in Pivotal Tracker 3 - Created AWS account; setup Elastic Beanstalk for Python web application; 5 - Discussing in Slack and thinking about what database we should use 6 - install pillow and redis on Mac | Time Spent [h] Task 0: 8; Time Spent [h] Task 1: 0.5; Time Spent [h] Task 3: 0.5; Time Spent [h] Task 5: 1 | 1.add user stories 2.learning django knowledge
4 | 9/26 - 10/2 | 10 | 10 | 0 | 0 - researching websocket for communication and try to build a demo. 0 - Watching some tutorials videos to learn back-end 7 - check the task assignament and sppp | Time Spent [h] Task 0: 10 | 1.check my part in sppp

## Misha
Name: Misha Chertushkin
Lead Roles: Security Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/5 - 9/11 | 0 | 0 | 0
2 | 9/12 - 9/18 | 6 | 4 | 2 | 0 - Read and took notes on the book, Chapters 1-4 0 - Researched the security issues in the AWS | Time Spent [h] Task 0: 4 | Pushed team.md in branch lab1
3 | 9/19 - 9/25 | 8 | 8 | 0 | 0 - Researched the security issues in the GCP 0 - Researched database options on GCP and AWS 3 - Set up the account on GCP 3 - Set up the PostgreSQL database on GCP 6 - Gave Access to the users of team 2 | Time Spent [h] Task 0: 4; Time Spent [h] Task 3: 3.5; Time Spent [h] Task 6: 0.5 | Merged lab1 branch into master Set up common accounts Filled SPP sections: Overview, Related Work
4 | 9/26 - 10/2 | 8 | 7 | 1 | 6 - Removed GCP and AWS accounts as we agreed to use Joe instances 2 - Designed Database schema for Application 3 - Implemented Database schema in PostgreSQL 5 - Joined Pivotal Tracker | Time Spent [h] Task 2: 2.5; Time Spent [h] Task 3: 3.5; Time Spent [h] Task 5: 0.5; Time Spent [h] Task 6: 0.5 | Created the design of DB and wrote the script in PostgreSQL

## Beven
Name: Beven Liu
Lead Roles: Configuration Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/5 - 9/11 | 0 |  |  | None. (Because I registered for this class in Sep 12th)
2 | 9/12 - 9/18 | 8 | 7 | 1 | 0 - Learned Git/GitHub, Python; Review lecture notes 6 - Set up project tools: Slack, GitHub, Pivotal tracker, Zoom, etc. Set environment: Python 7 - Complete the part of Configuration Management Plan in SPPP. | Time Spent [h] Task 0: 4; Time Spent [h] Task 6: 1; Time Spent [h] Task 7: 2 | 1 - Finish part of SPPP |  |  | 1 - Keep learning Python 2 - Keep reviewing lecture notes and reading textbook 3 - Start to learn web development(Not sure) | 8
3 | 9/19 - 9/25 | 9.5 | 8.5 | 1 | 0 - Learned knowledge about what a configuration learder should do from our textbook 0 - Watching some Django series in Youtube to learn this framework 5 - Discussing in Slack and thinking about what database we should use 7 - Joined the Pivotal Tracker | Time Spent [h] Task 0: 7; Time Spent [h] Task 5: 1; Time Spent [h] Task 7: 0.5 | 1 - Search some similar projects in github and learn from their experience 2 - Communicate with a senior and ask for some suggestions about making our task easier to realize | Have problems in back-end. |  | 1 - Keep learning Python 2 - Watch some tutorials about back-end and front-end, just ensure I can understand the basic framework | 5 (if workload is not too hard) or 2
4 | 9/26 - 10/2 | 10.5 | 10 | 0.5 | 0 - Study database. Read underlying programming code about SimpleDB and learn the basic framework. 0 - Watch some videos to learn back-end 0 - Learn how to create a PostgreSQL DB instance in AWS | Time Spent [h] Task 0: 10 | 1 - Updated one part of SPPP |  |  | 1 - Not sure because I have too much homework, but I will keep watching some tutorials | 2

## Jhuanderson
Name: Jhuanderson Macias
Lead Roles: Backup Project Leader, Requirement Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/5 - 9/11 | 1 | 1 | 1 | 5 - Setup Slack workspace, set up Pivotal Tracker 6 - Create Team 2 Respository on Github Clone folder and set up path and enviroment within person computer. pushed team.md commit to Lab1 branch 7 - Search for ideas involving communication. | Time Spent [h] Task 5: 0.25; Time Spent [h] Task 6: 0.25; Time Spent [h] Task 7: 0.5 | 1. Pushed team.md commit to Lab1 branch 2. Joined and learned Pivotal Tracker |  |  | 0 - Read chapters 13 - 15 1 - Define requirements and user stories, add to SPP 6 - Find time for a recurring team meeting | 5
2 | 9/12 - 9/18 | 4 | 2 | 2 | 0 - rearched Frameworks and BackEnd Configurations | Time Spent [h] Task 0: 2
3 | 9/19 - 9/25 | 13 | 12 | 1 | 0 - reasearch development vs prodcution enviroments 0- research real world exmaples by talking to software engineers about their process for devlopment 0 - research framework integrations 0 - reasearch databases - NOSQL vs SQL and its affects with our stack 6 - Created Docker enviroment that will be used for dev. ops 4 - Research Integrating testing tool (Jenkins) and its Integration with AWS 3 - started to build out simple protype of chat communication | Time Spent [h] Task 0: 4; Time Spent [h] Task 3: 2; Time Spent [h] Task 4: 1; Time Spent [h] Task 6: 5 | Basic Prototpy of Communciation tool Framework Set up Shared Resorces
4 | 9/26 - 10/2 |  | 7 | 1 | 0- Reasearch on different designs pattern and chose one that best fits our project 0 - Research Server Side Authentication 3 - complete single server side commuication application for demo 6 - Update Docker Enviroment to Ensure Proper Enviroment/Drafted best practices and how to use Pyton VENV 7. Update SDD Design and Key alogirthms currently in used / Create Stories & backfilled work done on Pivotal | Time Spent [h] Task 0: 2; Time Spent [h] Task 5: 1; Time Spent [h] Task 6: 1; Time Spent [h] Task 7: 2 | Single Serverside communication for LIve Demo |  |  | - Connect Application to our postgres database. Store and Retreive Data. | 15

## Hang
Name: Hang Shi
Lead Roles: Backup Team Leader, Requirements Leader
Week # | Start Date - End Date | Time Spent [h] |  |  | Tasks Completed 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Configuration/Environment 7 - Unclassified/Other | Time Spent [h] | [7 empty] | Project Deliverable Contribution(s) | Issues | Issue Status/Plan | Estimated Tasks for Next Week | Total Estimated Time for Next Week [h]
|  | Total | Individual Work | Group Meeting |  | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7
1 | 9/5 - 9/11 | 11 | 10 | 1 | 0 - learn from blackboard and list all element needed in this course 1 - set up team github and joined Pivotal Tracker and google drive 4 - Group github manage and verify access testing 5 - Join Slack team group, set up zoom video meeting configuration 6 - Setup GitHub Desktop client, committed team.md to Lab1 branch, add extra branch for team code testing and delete when we all finish, allocate all information on github quicktips.md for easily record and manage | 2 | 1 | 2 |  | 1 | 0.5 | 3.5 |  | 1 - Create github group 2 - Verify github group acess 3 - Compare and consider object of develop 4 - Test and create new branch for testing 5 - Merge and delete useless branch when all finish lab1 6 - Configuration help |  |  | 0 - learn from blackboard and relearn the github and web deisgn 1 - fill the SPPP requirement part and check more develop requirement 4 - Group github manage and merge test branch 5 - renew the allert in Slack avoid now receive messgae from group channel 6 - test and find out which platform or language using is best for group work | 10
2 | 9/12 - 9/18 | 7 | 7 | 0 | 0 - learn from blackboard and relearn the github and web deisgn 1 - fill the SPPP requirement part and check more develop requirement 4 - Group github manage and merge test branch 5 - renew the allert in Slack avoid now receive messgae from group channel 6 - test and find out which platform or language using is best for group work | 2 | 1 |  |  | 1 | 0.5 | 2.5 |  | 1 - Check the requirement for SPPP 2 - Analysis functional and nofunctional requirement 3 - Help finish slide and SPPP 4 - Update github group record 5 - Create new branch for testing | own problem not join group discussion but see record and finish my part |  | 0 - learn from blackboard and list all element needed in this course 1 - set up iOS new xcode programming platform 4 - test iOS xcode monitor 5 - learn online named: combine Django with Ios reatime feedback 6 - Setup dj back database test | 10
3 | 9/19 - 9/25 | 10 | 10 | 0 | 0 - learn from blackboard and list all element needed in this course 1 - set up iOS new xcode programming platform 4 - test iOS xcode monitor 5 - learn online named: combine Django with Ios reatime feedback 6 - Setup dj back database test | 3 | 1 |  |  | 3 | 2 | 1 |  | 1 - Check the requirement for SPPP 2 - Analysis functional and nofunctional requirement 3 - Help finish slide and SPPP 4 - Update github group record 5 - Create new branch for testing | seperate develop team as web and ios which i want to major in ios |  | 1 - iOS platform, login/logout, reset password user stories (Lab 2) 2 - iOS platform database primary key reset 3 - Fully finish all iOS supporting reg and login, etc. 5 - Order from team leader and give feedback of some need to change 6 - Updated project README.md, add more useful tips for team agile develop 7 - Update SPPP, SDD, Iteration 1 Presentation, Group Progress Report, Risk Management Worksheet | 13
4 | 9/26 - 10/2 | 15 | 7 | 8 | 1 - iOS platform, login/logout, reset password user stories (Lab 2) 2 - iOS platform database primary key reset 3 - Fully finish all iOS supporting reg and login, etc. 5 - Order from team leader and give feedback of some need to change 6 - Updated project README.md, add more useful tips for team agile develop 7 - Update SPPP, SDD, Iteration 1 Presentation, Group Progress Report, Risk Management Worksheet |  | 4 | 4 | 5 |  | 1 | 1 |  | 1 - Check the requirement for SPPP 2 - Analysis functional and nofunctional requirement 3 - Help finish slide and SPPP 4 - Update github group record 5 - Create new branch for testing | communicate problem and under too muach pressure |  |  | 10

## Metrics-GroupIterationProgress
Iteration | Start Date - End Date | # of User Stories Completed | # of User Stories in Progress | # of Issues Opened | # of Issues Closed | # of Issues Remaining | Time [h]
[7 empty] | Total | Individual Work | Group Meeting | Task 0 | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Total/Iteration
0 | 9/5 - 9/11 | 0 | 0 | 0 | 0 | 0 | 34 | 32 | 3 | 14 | 4.5 | 2 | 0 | 1 | 3.75 | 4.75 | 85
0 | 9/12 - 9/18 | 0 | 0 | 0 | 0 | 0 | 51 | 42 | 9 | 18 | 2 | 0 | 0 | 1 | 3.5 | 6.5
1 | 9/19 - 9/25 | 2 | 1 | 0 | 0 | 0 | 70 | 67 | 3 | 30 | 2.5 | 10 | 6 | 4 | 8 | 7 | 119.5
1 | 9/26 - 10/2 | 0 | 1 | 1 | 0 | 0 | 56 | 52.5 | 11.5 | 22 | 5 | 7 | 9.5 | 0 | 3.5 | 3.5
2
2
3
3
4
4
5
5

## Summary-GroupIterationProgress
Iteration | Start Date - End Date | Accomplishment Summary (i.e. User Stories, Tasks Completed, Big Progress, Good Practices Used, etc.) | Technical Issues Summary | Non-Technical Issues Summary | Process Improvement/Plan
0 | 9/5 - 9/11
1 | 9/12 - 9/18
2 | 9/19 - 9/25 | 1. Joe and Laura got skeleton application working. This application allows user registration, login/logout, and ability to join a chatroom where each user can send a message to the room. 2. Joe setup a configuration for a python virtualenv (requirements.txt) in GitHub. Team members will use this virtualenv for development so we share the same configuration. |  | 1. Group communication is not good.
3 | 9/26 - 10/2 | 1. Team members created user stories in Pivotal Tracker. 2. Opened first issues in GitHub issue tracker. 3. User stories associated with registration/login implemented. 4. Skeleton web app implemented in Django. | No known gating items at this time. AWS has a steep learning curve. | 1. Group communication is still being worked on and not yet resolved. Team members still seem confused about meeting times. | 1. Individuals tend to respond better when tasks are assigned directly to them, so tasks will be assigned this way moving forward. 2. Less experienced team members will not be expected to contribute immediately and will be paired with more experienced team members. 3. Communication in person and several days in advanced when the next meeting will be.
4
5