## Project Risk Status
ID | Risk Category | Risk Title | Risk Description | Owner | Probability [1-3] | Severity [1-3] | Risk Level [1-9] | Retirement Cost [h] | Mitigation Plan | Target Closure Date | Status [Open or Closed] | Notes
1 | Technolgy Competence | Not familiar with WebSocket | None of the team members have experience with Websocket | XI | 3 | 2 | 6 | 10 | Have all team members complete Django Channel tutorials | 2019-10-10 | Open
2 | Technolgy Competence | Not familiar with Django | None of the team members have experience with Djagno | - | 3 | 2 | 6 | 10 | Have all team members complete several Djagno tutorials | 2019-10-10 | Open
3 | Technolgy Competence | Not familiar with web development | Some of the team members have no experience with web development | - | 3 | 2 | 6 | 10 | Have all team members research web development independently | 2019-10-10 | Open
4 | Technolgy Competence | Little programming experience | Some of the team members have little or no computer science experience and cannot contribute immediately | - | 3 | 2 | 6 | 0 | Pair experienced members with inexperienced members | - | Open
5 | Technolgy Competence | Django-based server sometimes cannot easily give real-time feedback to client | Sometimes Django-based server side should need refresh to allocated the data from and database to show chat message | Joe | 2 | 3 | 6 | 4 | Use and learn some combination open-source structure (Django Channels) to put DJ and AWS together | 2019-10-10 | Open
6
6 | Technolgy Competence | iOS storyboard cannot reatime give out the error from ios13 to old version Xcode | Beacase of different people's xcode develop software, some icon can not show on the page in ios monitor | Hang | 3 | 2 | 6 | 4 | renew all developler's xcode and fix problem |  | Closed | have been finished and presenation for ios part using hang's laptop
7 | Personel | Loss of team members | One or more students may drop the class and leave the team | - | 2 | 2 | 4 | 0 | Another team member assumes role of the lost teammate | 2019-10-07 | Open | 10/7 is last day to drop a class without a W
8 | Management | Lack of motiviation or responsbility | One or more students may not contribute as expected to the project | Laura | 2 | 2 | 4 | 0 | Establish accountability with team members | 2019-10-03 | Open
9 | Technolgy Competence | Communication | Some students do not check Slack and/or email for updates on meeting times, deliverables, etc. | - | 2 | 2 | 4 | 0 | Establish a communication plan that works for everyone | - | Open
10 | Personel | Adding new team member | One or more students may join the class team and join the team | - | 2 | 1 | 2 | 0 | Give new team member one of the duplicate roles | 2019-09-16 | Closed | 9/16 is last day to add a class

## Risk Rating Criteria
Risk Rating Criteria
Probability |  |  | Severity
Rating | Likelihood | Description | Rating | Impact | Description
1 | Rare or Unlikely | Could occur at some point | 1 | Minor | Minor impact to project
2 | Possible | Might occur at some point | 2 | Moderate | Some impact to project
3 | Likely or Very Likely | Will likely occur at some point | 3 | Major | Major impact to project

## Risk Categories
Risk Categories
Management
Implementation
Testing
Integration
Deployment Rush
Specific Technical Issues
Improper Scope
Requirements
Communication
Personel
Technology Competence